## MAINTENANCE OF TRAFFIC.

(REV 7-24-23) (8-14-23) (10-23)

SUBARTICLE 102-3.3 is deleted and the following substituted:

**102-3.3 Lane Closures:** Approval for all lane closures, mobile operations, and traffic pacing operations is required. Submit routine requests to the Engineer 14 calendar days in advance of planned lane closures, mobile operations, and traffic pacing operations. Requests for planned lane closures are to be submitted through the Department’s Lane Closure Notification System (LCNS). For unforeseen events that require cancelling or rescheduling lane closures, mobile operations, and traffic pacing operations, revise the lane closure request as soon as possible.

Record information for lane closures, including but not limited to begin and end lane closure times and locations, into the Department’s LCNS. Lane closures are to be activated in the LCNS within five minutes of placing the first channelizing device and deactivated within 5 minutes removing the last channelizing device associated with the closure.

At the preconstruction conference, submit a request for access to the Department’s lane closure notification system to the Engineer. Include the name, email address, level of access required, and a copy of the individual’s certification of training for Contractor personnel requiring access to the Department’s LCNS. For change of access requests, submit a request to the Engineer at least ten calendar days in advance of when the change is needed.

**102-3.3.1 Traffic Pacing:** In addition to dates and locations, include a pacing plan outlining the expected equipment and number of traffic control officers required, the proposed traffic pacing lengths and durations, the available existing egresses in the event of an emergency, and a contingency plan in the event of an equipment failure.